## Slide 1: Half yearly review
Ashok Kumar
ETD

## Slide 2
A. Progress of NWIPs and Reviews against the Annual Action Plan for 2024-25 - with break-up of Archived, Withdrawn, Reaffirmed, Amended and Revised. B. Process adopted for the NWIPs - ARP, WG, R&D, Seminars/workshops.
Committee | Title | Status | Process
ETD 07 - Low Voltage Switchgear And Controlgear | DC Switchgear | P-Draft | ETD 07/WP-2
 | Applicability of the general rules to RCBOs functionally independent of line voltage | Draft under consideration | Draft at IEC is under preparation. 1 Expert nominated in the corresponding WG of IEC committee. To be further discussed in committee
 | Type F and Type B residual current operated circuit-breakers with and without integral overcurrent | Draft under consideration | Draft at IEC is under preparation. 1 designated expert has been identified. Inputs sought from CPRI and ERDA to confirm the testing facility. To be further discussed in committee
 | Voltage dependent Type AC and Type A RCBO | Draft under consideration | Draft at IEC is under preparation. 1 Expert nominated in the corresponding WG of IEC committee. To be further discussed in committee
 | Low-voltage switchgear and controlgear - Ancillary equipment - Terminal blocks for copper conductors | F-draft | ETD 07/WP-1
 | Low-voltage switchgear and controlgear - Ancillary equipment - Protective conductor terminal blocks for copper conductors | F-draft | ETD 07/WP-1

## Slide 3
Sectional Committee | NWIP | NWIP Status
ETD 07 | 6 | P draft – 1 F draft – 2 Allotted to WP - 3

## Slide 4
Sectional Committee | Standards due for review | No. of Standards Reviewed | Review underway | Review Pending | Action completed based on review | Outcome of the review |  |  | 
 |  |  |  |  |  | Revision | Archive | Reaffirmation | Withdraw
ETD 07 | 06 (3 Pre-2000) | 5 | 1 (Pre-2000) | 0 | 5 | - | 1 (proposed) | 3 | 2
A. Progress of NWIPs and Reviews against the Annual Action Plan for 2024-25 - with break-up of Archived, Withdrawn, Reaffirmed, Amended and Revised.

## Slide 5
C. Process adopted for the Reviews - ARP, WG, R&D, Workshop.
D. Indicate clearly the projects done without ARP or WG.
Committee | IS No | Process Adopted | Status | Remark
ETD 07 | IS 13032 : 1991 | WP-2 | Approved for withdrawal | 
 | IS 5039 : 1983 | WP-2 | Approved for withdrawal | 
 | IS 8588 : Part 1 : 1977 | - | Decision taken to Reaffirm and Archive | 
 | IS 17122 : 2019 | - | Reaffirmed | IEC is identical and in use.
 | IS/IEC 60898 : Part 3 : 2019 | - | Reaffirmed | IEC is identical and in use.
 | IS/IEC 60947 : Part 5 : Sec 2 : 2019 | - | Reaffirmed | IEC is identical and in use.

## Slide 6
E. Working Panels and Working Groups - Created, abolished, updated on Advance Dashboard.
Following Working groups/Panels have been created for each committee. Revisions are being prepared by the WGs/Panels as well
ETD Committee | Working Group/Working Panel | Title | No. of Experts | Task Assigned
ETD 07 | WP-1 | Review of IEC TC 121 and SC 121A ballot documents and Standards Panel | 6 | The panel is responsible for reviewing and providing expert input on ballot documents and standards developed under IEC TC 121 and IEC SC 121A. This includes evaluating proposed international standards related to low-voltage switchgear and controlgear, ensuring alignment with national regulations and industry needs, and proposing any necessary revisions or updates.
 | WP-2 | Review of IEC SC 121B ballot documents Panel | 6 | The panel is responsible for reviewing and providing expert input on ballot documents and standards developed under IEC SC 121B. This includes evaluating proposed international standards related to low-voltage switchgear and controlgear, ensuring alignment with national regulations and industry needs, and proposing any necessary revisions or updates.
 | WP-3 | Review of IEC SC 23E ballot documents Panel | 5 | The panel is responsible for reviewing and providing expert input on ballot documents and standards developed under IEC SC 23E. This includes evaluating proposed international standards related to low-voltage switchgear and controlgear, ensuring alignment with national regulations and industry needs, and proposing any necessary revisions or updates.

## Slide 7
Following SECTORS/SUB-SECTORS are PROPOSED under each committee. WGs/Panels shall be re-aligned after discussion with committee
Subject Area | Sectors
ETD 07 - Low Voltage Switchgear And Controlgear | Switchgear and controlgear equipment
 | Switchgear and controlgear assemblies
 | Circuit-breakers and similar equipment for household use

## Slide 8
F. ISO/IEC Projects - Identified in H & M category, experts designated, strategies adopted to identify experts.
New Projects (NP) at IEC | Title of the Project | Level of Interest (High/Medium/Low) | TC/SC | WG/MT/PT | Whether Expert has been designated | Name of the Expert (If expert has been designated)
23E/1343/NP | Residual current operated circuit-breakers for household and similar uses for dc systems - Part 2: Residual current operated circuit breakers without integral overcurrent protection (DC-RCCBs) |  | IEC SC 23E |  | No | -
23E/1316/NP | Protective devices based on semiconductor technology for household and similar use - Part 1: Semiconductor Residual current operated Circuit-Breakers with integral Overcurrent protection for household and similar uses (SC-RCBOs) |  | IEC SC 23E |  | No | -
23E/1356/CD | Residual direct current detecting device (RDC-DD) to be used for mode 3 charging of electric vehicles |  | IEC SC 23E | WG 8 | No | -
121/122/CD | Low-voltage switchgear and controlgear - Product data and properties for information exchange - Part 1: Catalogue data |  | IEC TC 121 | WG 3 | Yes | Mr Chandrashekhar Kore
121/168/CD | Switchgear and controlgear and their assemblies for low voltage - Environmental aspects |  | IEC TC 121 | WG 2 | No | -
121/167/CD | Switchgear and controlgear and their assemblies for low voltage - Security aspects |  | IEC TC 121 | WG 4 | Yes | Mr Rahul Srivastava

## Slide 9
F. ISO/IEC Projects - Identified in H & M category, experts designated, strategies adopted to identify experts.
New Projects (NP) at IEC | Title of the Project | Level of Interest (High/Medium/Low) | TC/SC | WG/MT/PT | Whether Expert has been designated | Name of the Expert (If expert has been designated)
121A/586A/CD | Low-voltage switchgear and controlgear - Part 1: General rules |  | IEC SC 121A | MT 5 | No | -
121A/614/CD | Low-voltage switchgear and controlgear - Part 5-3: Control circuit devices and switching elements - Requirements for proximity devices with defined behaviour under fault conditions (PDDB) |  | IEC SC 121A | WG 3 | No | -
121A/594/CD | Low-voltage switchgear and controlgear - Part 6-1: Multiple function equipment - Transfer switching equipment |  | IEC SC 121A | MT 18 | No | -
121A/570/CD | Fragment 1 - Low-voltage switchgear and controlgear - Part 7-1: Ancillary equipment - Terminal blocks for copper conductors |  | IEC SC 121A | MT 8 | Yes | Mr Robin Virani
121A/622/CD | Low-voltage switchgear and controlgear - Part 7-2: Ancillary equipment - Protective conductor terminal blocks for copper conductors |  | IEC SC 121A | MT 8 | Yes | Mr Robin Virani
121A/565/CD | Low-voltage switchgear and controlgear – Part 10: Semiconductor Circuit-Breakers |  | IEC SC 121A | PT 60947-10 | Yes | Mr Tanmay Tamboli
121A/623/CD | Low-voltage switchgear and controlgear - Controllers for drivers of stationary fire pumps |  | IEC SC 121A | MT 20 | No | -
121B/186/CD | Low-voltage switchgear and controlgear assemblies - Part 6: Busbar trunking systems (busways) |  | IEC SC 121B | MT 3 | No | -
121B/201/CD | Low-voltage switchgear and controlgear assemblies - Internal arc-fault protection of low-voltage switchgear and controlgear assemblies in accordance with the IEC 61439 series |  | IEC SC 121B | PT 61641 | No | -

## Slide 10: H. Status of Process Reform measures - Attendance, Inactive members, Comments on P Drafts, Resolutions, members trained, SC membership rationalised.
Entire process reform have been circulated to members along with handbook for TC members and included in agenda of meetings held.
Attendance - inactive members - Members who have not attended 2 consecutive meetings have been removed.
Comments on P/WC Drafts- P/WC drafts circulated-8, No of comments - 9
Resolutions – Circulated to members within 24 hrs of meetings
SC membership rationalisation – Being taken up in SC meetings