## Slide 1: Half Yearly Review Meeting Rajesh Choudhary Scientist ‘B’ (MS: CED 03, CED 22, & CED 36)
18 October 2024

## Slide 2: Process adopted for the NWIPs
Committee | NWIP | Received from | Process | Status
CED 36 | Fire and life safety audit | Committee | WP | Working draft under preparation.
CED 36 | Fire safety in hospitals | Committee | WP | Working draft under preparation.
CED 36 | ASTM E84 Surface Burning Characteristics of Building Materials | Ministry | WG | Working draft under preparation.
CED 36 | Fire tests on building materials and structures (BS 476 series) | Ministry | - | BIS has already adopted various parts of ISO 834 on the same subject.
CED 36 | Performance of the spandrel panel assembly during the standard fire-exposure conditions | Committee | Committee | Working draft prepared.
CED 36 | Fire Resistance of Building Joint Systems | Committee | Committee | Working draft prepared.

## Slide 3: Process adopted for the NWIPs
Committee | NWIP | Process | Status
CED 36 | Fire resistance of vertical and horizontal ventilation ducts under standardized fire conditions (ISO 6944) | Ministry | -
CED 36 | EN 12101-6 Smoke and heat control systems - Specification for pressure differential systems. Kits | Ministry | -
CED 36 | Standard for Safety Smoke Dampers (UL 555S) | Ministry | -
CED 36 | Safety arrangement for Electrical Fire and flood hazards in Hydro power plants | Ministry | -
CED 36 | Fire Dampers for Air Distribution Systems (based on ISO 21925 – 2:2019) | Ministry | -
CED 36 | Smoke and Heat Control Systems (ISO 21927-3), | Ministry | -
CED 36 | EN 12106-3 Smoke and heat control systems - Part 3: Specification for powered smoke and heat control ventilators (Fans) | Ministry | -

## Slide 4: Process adopted for the Reviews
Committee | R&D | Intern | WG/WP | ARP
CED 36 | 0 | 0 | 4 | 0

## Slide 5: Process adopted for the Reviews
Committee | Subject | Mode of Execution | Status
CED 36 | IS 3594: 2024 Fire Safety of General Storage and Warehousing Including Cold Storages - Code of Practice (second revision) | WG | Published
CED 36 | Fire Protection of Electronic Data Processing Installation (second revision of IS 12456) | WP | Draft is being prepared.
CED 36 | IS 13716 Fire Safety in Hotels – Code of Practice (first revision of IS 13716) | WP | Draft is being prepared.
CED 36 | Method for classification of flame spread of products (first revision of IS 12777) | WG | Draft is being prepared.

## Slide 6: Progress of Reviews against the Annual Action Plan for 2024-25
Committee | Review Taken in APS | Due for Review |  |  |  |  | Other |  |  |  |  | Pending
 |  | Revised | Amended | Archived | Reaffirmed | Withdrawn | Revised | Amended | Archived | Reaffirmed | Withdrawn | 
CED 36 | 22+10 | 1 | 0 | 11 | 8 | 1 | 1 | 0 | 0 | 0 | 0 | 10

## Slide 7: Progress of Reviews against the Annual Action Plan for 2024-25
Revised
Committee | IS No. | Title | Remark
CED 36 | IS 3594: 2024 | Fire Safety of General Storage and Warehousing Including Cold Storages - Code of Practice (Second Revision) | Published
CED 36 | IS 12459 : 2024 | Fire Safety in Cable Runs - Code of Practice (First Revision) | Published

## Slide 8: Progress of Reviews against the Annual Action Plan for 2024-25
Archived
Committee | IS No. | Title
CED 36 | IS 13694:1993 | Fire safety in iron and steel industries ― Code of practice
CED 36 | IS 2726:1988 | Code of practice for fire safety of industrial buildings: Cotton ginning and pressing (including cotton seed delintering) factories (first revision)
CED 36 | IS 4226:1988 | Code of practice for fire safety of industrial buildings: Aluminium/Magnesium powder factories (first revision)
CED 36 | IS 8758:2013 | Fire precautionary measures in construction of temporary structures and pandals ― Code of practice (second revision)
CED 36 | IS 12458:2019 | Fire resistance of through penetration firestops — Method of Test (first revision)
CED 36 | IS 14435:2013 | Fire safety in educational institutions ― Code of practice (first revision)
CED 36 | IS 14689:1999 | Code of practice for fire safety in industrial buildings (printing and publishing industry)
CED 36 | IS/ISO 834-4:2000 | Fire-resistance tests – Elements of building construction: Part 4 Specific requirements for load bearing vertical separating elements
CED 36 | IS/ISO 834-5:2000 | Fire-resistance tests – Elements of building construction: Part 5 Specific requirements for load bearing horizontal separating elements
CED 36 | IS 4886:1991 | Fire safety of industrial buildings: Tea factories ― Code of practice (first revision)
CED 36 | IS 13045:1991 | Code of practice for fire safety of industrial buildings– Flour mills

## Slide 9: Process adopted for the Reviews
Working Panels and Working Groups Created
CED 36 : P1 Panel for the Revision of IS 12456 Fire Safety of Data Centres
CED 36 : P2 Panel for the Formulation of New Indian Standard on Fire and Life Safety Audit
CED 36 : P3 Panel for Revision of IS 13716 ‘Fire Safety in Hotels – Code of Practice’
CED 36 : P4 Panel for New Indian Standard on Fire Safety of Healthcare Premises

## Slide 10: ISO/IEC Projects - Identified in H & M Category, Experts Designated, strategies adopted to identify experts
Subject | Expert Designated | H&M Category | Strategy Adopted
Standardized Post-Fire Data Collection Methods from Large Outdoor Fires, ISO/NP 24944 | Dr G C Misra, Member CED 36 | M | Based on the profile of the member & discussion in the technical Committee
Call for Convenor of ISO/TC 92/TG 2: Fire Fighters | Shri R C Sharma, Member CED 36 | M | Based on the profile of the member & discussion in the technical Committee
Call for Convenor of ISO/TC 92/WG 15 :Fire Safety for Tunnels | Dr K. C. Wadhwa, Member CED 36 | H | Based on the profile of the member & discussion in the technical Committee

## Slide 11: Status of Process Reform Measures - Attendance, Inactive Members, Comments on P Drafts, Resolutions, Members Trained, SC membership rationalised.
Committee | Meeting No. | Attendance | Inactive Members removed | Resolutions
CED 36 | 33rd | 85.19% | - | Uploaded

## Slide 12: Status of Process Reform Measures - Attendance, Inactive Members, Comments on P Drafts, Resolutions, Members Trained, SC membership rationalised.
Committee | Industry Association | Regulatory Body | State Government | R&D Organization | Academic Institution | Expert | Industry | Consumer Group | Central Ministry/Dept. | Technologist | Unclassified | Total
CED 36 | 1 | 0 | 0 | 2 | 1 | 3 | 4 | 7 | 2 | 8 | 0 | 28

## Slide 13: SC Meeting/Seminar Planned Outside HQ
Committee | Date | Meeting Planed outside HQ
Fire Safety Sectional Committee, CED 36 | 13 December 2024 | IIT Gandhinagar

## Slide 14
Thank You