## Slide 1: HALF YEARLY REVIEW OF TECHNICAL COMMITTEES – CHD 05, CHD 09 & CHD 27
Presented by: Puja Priya
Scientist-D, CHD

## Slide 2: Progress of AAP 2024-25 – “NWIP”
Committee | Subject | Status of Draft Standard | Process Adopted
CHD 05 | Photography — Photographic-grade chemicals — Test methods — Part 1: General | The draft standard is under WC Stage. | By ARP
CHD 05 | Photography — Photographic-grade chemicals — Test methods — Part 2: Determination of matter insoluble in water | The draft standard is under WC Stage. . | By ARP
CHD 05 | Photography — Photographic-grade chemicals — Test methods — Part 3: Determination of matter insoluble in ammonium hydroxide solution | The draft standard is under WC Stage. | By ARP
CHD 05 | Photography — Photographic-grade chemicals — Test methods — Part 4: Determination of residue after ignition | The draft standard is under WC Stage. | By ARP
CHD 05 | Photography — Photographic-grade chemicals — Test methods — Part 5: Determination of heavy metals and iron content | The draft standard is under WC Stage. | By ARP

## Slide 3: Progress of AAP 2024-25 – “NWIP”
Committee | Subject | Status of Draft Standard | Process Adopted
CHD 05 | Photography — Photographic-grade chemicals — Test methods — Part 6: Determination of halide content | The draft standard is under WC Stage. | By ARP
CHD 05 | Photography — Photographic-grade chemicals — Test methods — Part 7: Determination of alkalinity or acidity | The draft standard is under WC Stage. . | By ARP
CHD 05 | Photography — Photographic-grade chemicals — Test methods — Part 8: Determination of volatile matter | The draft standard is under WC Stage. | By ARP
CHD 05 | Photography — Photographic-grade chemicals — Test methods — Part 9: Reaction to ammoniacal silver nitrate | The draft standard is under WC Stage. | By ARP
CHD 05 | Photography — Photographic-grade chemicals — Test methods — Part 10: Determination of sulfide content | The draft standard is under WC Stage. | By ARP

## Slide 4: Progress of AAP 2024-25 – “NWIP”
Committee | Subject | Status of Draft Standard | Process Adopted
CHD 05 | Photography — Photographic-grade chemicals — Test methods — Part 11: Determination of specific gravity | The draft standard is under WC Stage. | By ARP
CHD 05 | Photography — Photographic-grade chemicals — Test methods — Part 12: Determination of density | The draft standard is under WC Stage. . | By ARP
CHD 05 | Photography — Photographic-grade chemicals — Test methods — Part 13: Determination of pH | The draft standard is under WC Stage. | By ARP
CHD 09 | Clay Utensils - Specification | The draft standard is under WC Stage. | By Working group
CHD 27 | Fire Performance for Thermal Insulation Materials to be Used in Building Equipment or Building Structures - Method of Test | The draft standard is under P Draft Stage. | By Working group

## Slide 5: Progress of AAP 2024-25 – “NWIP”
Committee | Subject | Status of Draft Standard | Process Adopted
CHD 27 | Thermal Insulation for Building Equipment Industrial Installations - Calculation Rules | Published | By Working Panel
CHD 27 | Thermal insulation Determination of steady-state thermal transmission properties of thermal insulation for circular pipes | under Publication | By Working Panel
CHD 27 | Rigid Cellular Plastics -Thermal Insulation Products for Buildings - Extruded Polystyrene (XPS) Insulation Board Specification | Under development | By Working Panel
CHD 27 | Thermal insulation products - Aerogel blanket- Specification | The draft standard is under P Draft Stage. | By Working Panel
CHD 27 | Flexible Elastometric Foam (Fef) Products for Thermal Insulation of Building Equipment, Building Structures and Industrial Application - Specification | Under development | By Working Panel

## Slide 6: Progress of AAP 2024-25 – “Carried Over Reviews”
Total number of Carried-Over “Pre-2000 Standards” for Review(CHD 05)
Archived-0
Published-18 (through ARP)
Withdrawn-0
Under WC-2
Under Publication- 6 (through ARP)
Amended-0

## Slide 7: Progress of AAP 2024-25 – “Carried Over Reviews”
Total number of Carried-Over “Pre-2000 Standards” for Review (CHD 09)
Archived-0
Published-2 (through ARP)
Withdrawn-0
Under WC-8 (through working panels)
Under Publication- 2 (through working panels)
Amended-0

## Slide 8: Progress of AAP 2024-25 – “Carried Over Reviews”
Total number of Carried-Over “Pre-2000 Standards” for Review (CHD 27)
Archived-0
Published-5 (through working panels)
Withdrawn-0
Under WC-3 (through working panels)
Under Publication- 4 (through working panels)
Amended-0
Under P Draft stage- 2 (through working panels)

## Slide 9: Progress of AAP 2024-25 – “Carried Over Reviews”
Committee | Subject / IS | Status of Draft Standard | Process Adopted
CHD 05 | IS 10982 : 1984 Strontium Sulphate for Electroplating — Specification | The draft standard is under WC stage. | ARP allocated to BIS Officer.
CHD 05 | IS 12201 : 1987 Hydrofluosilicic Acid for Electroplating — Specification | The draft standard is under WC stage. | ARP allocated to BIS Officer.
CHD 05 | IS 5003: 1968 Cadmium Oxide For Electroplating — Specification | The draft standard is under Publication. | ARP allocated to BIS Officer.
CHD 05 | IS 6358: 1971 Potassium and Sodium Cyanides for Electroplating - Specification | The draft standard is under Publication. | ARP allocated to BIS Officer.

## Slide 10: Progress of AAP 2024-25 – “Carried Over Reviews”
Committee | Subject / IS | Status of Draft Standard | Process Adopted
CHD 05 | IS 11484: 1985 Phenol Sulphonic Acid For Electroplating — Specification | The draft standard is under Publication. | ARP allocated to BIS Officer.
CHD 05 | IS 7067: 1973 Fluoboric Acid And Metal Fluoborates For Electroplating — Specification | The draft standard is under Publication. | ARP allocated to BIS Officer.
CHD 05 | IS 4847: 2006 Copper Salts For Electroplating — Specification | The draft standard is under Publication. | ARP allocated to BIS Officer.
CHD 05 | IS 6267: 1971 Silver Cyanide and Silver Potassium Cyanide for Electroplating -—Specification | The draft standard is under Publication. | ARP allocated to BIS Officer.

## Slide 11: Progress of AAP 2024-25 – “Carried Over Reviews”
Committee | Subject / IS | Status of Draft Standard | Process Adopted
CHD 09 | IS 3972 : Part 2 : Sec 8: 1990 Vitreous and Porcelain Enamelled Manufactured Articles — Determination of Resistance | The draft standard is under Publication. | ARP allocated to BIS Officer.
CHD 09 | IS 3972 : Part 2 : Sec 12: 1999 Methods of test for Vitreous Enamelware Part 2 Test methods Section 12 Resistance to torsion (Second Revision) | The draft standard is under Publication. | ARP allocated to BIS Officer.
CHD 09 | IIS 3972 : Part 2 : Sec 11: 1995 Vitreous Enamelware Part 2 Test Methods Section 11 Resistance to Abrasion ( Second Revision ) | Published | ARP allocated to BIS Officer.
CHD 09 | IS 12038 : Part 1: 2007 Vitreous and porcelain enamels - Release from enamelled articles in contact with food - Methods of test and limits second revision | Published | ARP allocated to BIS Officer.

## Slide 12: Progress of AAP 2024-25 – “Carried Over Reviews”
Committee | Subject / IS | Status of Draft Standard | Process Adopted
CHD 09 | IS 2333: 1992 Plaster of Paris for Ceramic and Glass Industry - Specification (Third Revision) | The draft standard is under WC Stage. | ARP allocated to BIS Officer.
CHD 09 | IS 2838: 1964 Stoneware Containers for General Purposes - Specification (First Revision) | The draft standard is under WC Stage. | ARP allocated to BIS Officer.
CHD 09 | IS 2839: 1964 Industrial Stoneware - Specification (First Revision) | The draft standard is under WC Stage. | ARP allocated to BIS Officer.

## Slide 13: Progress of AAP 2024-25 – “Carried Over Reviews”
Committee | Subject / IS | Status of Draft Standard | Process Adopted
CHD 27 | IS 13286: 1992 Surface Spread of Flame for Thermal Insulation Materials - Methods of Test (First Revision) | The draft standard is under WC Stage. | ARP allocated to BIS Officer.
CHD 27 | IS 12432 : Part 1: 1988 Application of spray applied insulation Code of practice: Part 1 Mineral fibre | The draft standard is under WC Stage. | ARP allocated to BIS Officer.
CHD 27 | IS 11307: 1985 Cellular Glass Block and Pipe Thermal Insulation - Specification First revision | The draft standard is under WC Stage. | ARP allocated to BIS Officer.
CHD 27 | IS 18973 : 2024/ ISO 8497 Thermal Insulation — Determination of Steady-State Thermal Transmission Properties of Thermal Insulation for Circular Pipes | The draft standard is under Publication. | ARP allocated to BIS Officer.

## Slide 14: Progress of AAP 2024-25 – “Carried Over Reviews”
Committee | Subject / IS | Status of Draft Standard | Process Adopted
CHD 27 | IS 11239 : Part 8: 1985 Rigid Cellular Thermal Insulation Materials - Methods of Test - Part 8 Flame Height, Time of Burning and Loss of Mass (First Revision) | The draft standard is under Publication. | ARP allocated to BIS Officer.
CHD 27 | IS 12432 : Part 2: 1999 Application of Spray Applied Insulation - Code of Practice: Part 2 Calcium Silicate (First Revision) | The draft standard is under Publication. | ARP allocated to BIS Officer.
CHD 27 | IS 11239 : Part 11: 1985 Rigid Cellular Thermal Insulation Materials - Methods of Test - Part 11 Compressive Strength (First Revision) | The draft standard is under Publication. | ARP allocated to BIS Officer.
CHD 27 | IS 3144 : 2024 Mineral Wool Thermal Insulation Materials - Method of Test (Third Revision) | Published | ARP allocated to BIS Officer.

## Slide 15: Progress of AAP 2024-25 – “Carried Over Reviews”
Committee | Subject / IS | Status of Draft Standard | Process Adopted
CHD 27 | IS 11308 : 2024 Hydraulic Setting Thermal Insulating Castables for Temperatures up to 1 250 °C — Specification (First Revision) | Published | ARP allocated to BIS Officer.
CHD 27 | IS 13204 : 2024 Rigid Phenolic Foam for Thermal Insulation - Specification (First Revision) | Published | ARP allocated to BIS Officer.
CHD 27 | IS 18652 : 2024 ISO 12241 : 2022 Thermal Insulation for Building Equipment and Industrial Installations Calculation Rules | Published | ARP allocated to BIS Officer.
CHD 27 | IS 9428 : 2024 Preformed Calcium Silicate Insulation (For Temperature up to 950 °C) — Specification (Second Revision) | Published | ARP allocated to BIS Officer.

## Slide 16: Progress of AAP 2024-25 – “ Current Reviews”
Total number of Standard under review – current 46 (CHD 05)
Archived-28
Withdrawn-0
Reaffirmed-0
Amended-0
Revised-8 (through ARP)
Under Review – 10 (through ARP)

## Slide 17: Progress of AAP 2024-25 – “Current Reviews”
Total number of Standard under review – current -19 (CHD 09)
Archived-0
Withdrawn-0
Reaffirmed-0
Amended-0
Revised-0
Under Review – 19 (through WPs)

## Slide 18: Progress of AAP 2024-25 – “Current Reviews”
Total number of Standard under review – current 22 (CHD 27)
Archived- 0
Withdrawn-0
Reaffirmed- 9 (through ARP)
Amended-0
Under Revision- 9 (through ARP)
Under Review – 4 (through ARP)

## Slide 19: Progress of AAP 2024-25 – “Current Reviews”
Committee | Subject / IS | Status of Draft Standard | Process Adopted
CHD 05 | IS 13443 : 1992 Methylene chloride for degreasing prior to electroplating - Specification | Under Preparation | ARP allocated to Shri Mohit Meena
CHD 05 | IS 1880 : 1977 Specification for zinc oxide and zinc salts for electroplating (First Revision) | Under Preparation | ARP allocated to Shri Mohit Meena
CHD 05 | IS 2214 : 1977 Specification for silver nitrate, pure and analytical reagent (First Revision) | Under Preparation | ARP allocated to Shri Mohit Meena
CHD 05 | IS 12551 : 1988 Specification for potassium pyrophosphate for electroplating | Under Preparation | ARP allocated to Ms. Divya Choudhary

## Slide 20: Progress of AAP 2024-25 – “ Current Reviews”
Committee | Subject / IS | Status of Draft Standard | Process Adopted
CHD 05 | IS 10472 : 1983 Specification for filter aid powder for use in electroplating | Under Preparation | ARP allocated to Shri Ankit Bhumla
CHD 05 | IS 12519 : 1988 Specification for zinc pyrophosphate for electroplating | Under Preparation | ARP allocated to Shri Ankit Bhumla
CHD 05 | IS 13014 : 1990 Sodium gluconate for electroplating - Specification | Under Preparation | ARP allocated to Shri Ankit Bhumla
CHD 05 | IS 12557 : 1988 Specification for sodium pyrophosphate for electroplating | Under Preparation | ARP allocated to Ms. Divya Choudhary

## Slide 21
Sectional Committee | No. of existing Working Panels and Working Groups | Title of Working Panels (WP) and Working Groups (WG) | No. of Working Panels/Groups created | No. of Working Panels/Groups abolished | Plan of Action
CHD 09 | Working Panels-7 Working Group-0 | Metallic and Other Inorganic coatings Panel Ceramicware, Glassware and Glass Ceramicware in contact with food Panel Fine Ceramics Panel Raw Material Panel Chemical and Physical parameters of Opacifier Panel Waste Material Panel Alert Panel | Working Panels-0 Working Groups-0 | Working Panels-0 Working Groups-0 | Working Panels/Groups will be restructured in line with the sectorial classification of the Sectional Committees.
WORKING PANELS AND WORKING GROUPS

## Slide 22: WORKING PANELS AND WORKING GROUPS
Sectional Committee | No. of existing Working Panels and Working Groups | Title of Working Panels (WP) and Working Groups (WG) | No. of Working Panels/Groups created | No. of Working Panels/Groups abolished | Plan of Action
CHD 27 | Working Panels-5 Working Groups-0 | To prepare the strategic roadmap of CHD 27 for 5 years. For revision of standards related to foam based thermal insulation material Panel Preparation of P-draft of Thermal insulation product — Aerogel Panel To provide inputs on ISO ballots and other related ISO activities Panel To work on developing standards on new test methods Panel | Working Panels-2 Working Groups-0 | Working Panels-2 | Working Panels/Groups will be restructured in line with the sectorial classification of the Sectional Committees.

## Slide 23: Sectional Committees Meetings Held
Sl. No. | Committee | First Half of Year | 
 |  | Meeting Venue | Date of Meeting
1 | CHD 05 | Virtual Meeting (New Delhi, Delhi, India) | 30 July 2024
2 | CHD 09 | Virtual Meeting (New Delhi, Delhi, India) | 8 July 2024
3 | CHD 27 | Virtual Meeting (New Delhi, Delhi, India) | 30 July 2024

## Slide 24: Sectional Committees Meetings Planned
Sl No. | Committee | 3rd Quarter |  | 4th Quarter | 
 |  | Meeting Venue | Date of Meeting | Meeting Venue | Date of Meeting
1 | CHD 05 | CSIR - Central Electrochemical Research Institute, Karaikudi | 3 Dec 2024 | Hybrid Meeting (New Delhi, Delhi, India) | 25 Feb 2024
2 | CHD 09 | CSIR - Central Glass and Ceramic Research Institute, Kolkata | 26 Nov 2024 | Hybrid Meeting (New Delhi, Delhi, India) | 4 Feb 2024
3 | CHD 27 | CSIR - Central Building Research Institute, Roorkee | 10 Dec 2024 | Hybrid Meeting (New Delhi, Delhi, India) | 20 March 2024

## Slide 25: ISO Projects (NP, CD & DIS Ballots)
ISO | NMC | Ballot type | Title of the Project | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 163/ SC 1 | CHD 27 | ISO/NP 9900 | Thermal insulation — Determination of thermal conductivity by Guarded Hot Plate Method at elevated temperature from 100 °C to 800 °C | Medium | Dr Punit Kumar | Committee decision

## Slide 26
ISO | NMC | Ballot type | Title of the Project | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 163/ SC 1 | CHD 27 | ISO/DIS 16685 | Thermal insulating products for industrial installations — Mechanical properties testing at sub-ambient temperatures | High | Dr Punit Kumar | Committee decision
ISO Projects (NP, CD & DIS Ballots)

## Slide 27: ISO Projects (NP, CD & DIS Ballots)
ISO | NMC | Ballot type | Title of the Project | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 163/ SC 3 | CHD 27 | ISO/DIS 18959 | Thermal insulation products — Rigid nano-microporous insulation for industrial applications — Specification | Medium (M) | Nil | Yet to be identified
TC 163/ SC 3 | CHD 27 | ISO/DIS 20812 | Thermal insulation products for buildings — Cellular glass products — Specification | Medium (M) | Nil | Yet to be identified

## Slide 28: Status of process reform measures
Attendance in sectional committee meetings
Inactive Members- Identified after every sectional committee meeting and removed if found absent in two consecutive meetings.
Comments on p-drafts- 2 P Draft document of CHD 27 were circulated.
Members trained- New members (10) inducted in the committee are trained as and when trainings are conducted by NITS.
SC membership rationalized- evaluation of performance of committee members has been done based on Attendance, Comments on Drafts circulated, Comments on ISO documents circulated, contribution during the meetings based on which decision on membership will be taken during the upcoming sectional committee meetings.
Sectional Committee | Attendance in Q1 | Attendance in Q2
CHD 05 | Nil | 45.45 %
CHD 09 | Nil | 50 %
CHD 27 | Nil | 65 %