## Slide 1: Half yearly review
ABINASH BORDOLOI
MEMBER SECRETARY- ETD 02, ETD 16 & ETD 34

## Slide 2: PROGRESS OF NWIP’S AGAINST THE ANNUAL ACTION PLAN FOR 2024-2025 AND THE PROCESS ADOPTED
SECTIONAL COMMITTEE | SUBJECT/TITLE OF NWIP | STATUS | PROCESS
ETD 02-Solid Electrical Insulating Materials & Systems | Vulcanized Fibre for Electrical Purposes-Part 1 Definitions and General Requirements | Published | Working Panel P04
 | Vulcanized Fibre for Electrical Purposes-Part 2 Methods of Test | Published | Working Panel P04
 | Vulcanized Fibre for Electrical Purposes-Part 3 Individual Materials specification Section 1 Flat Sheets | Published | Working Panel P04
 | Heat Shrinkable Sleeves and testing | Under Review | Working Panel P02
ETD 16-Transformers | Inverter Duty Transformers | Working Draft under Preparation | Working Panel P07
 | Submersible Duty Transformers and Accessories | Working Draft under Preparation | Working Panel P06

## Slide 3: PROGRESS OF NWIP’S AGAINST THE ANNUAL ACTION PLAN FOR 2024-2025 AND THE PROCESS ADOPTED
SECTIONAL COMMITTEE | SUBJECT/TITLE OF NWIP | STATUS | PROCESS
ETD 16-Transformers | Dry Type Distribution Transformers | Working draft under preparation | Working Panel P10
 | Tap Changers-Application Guidelines | Working draft under preparation | Working Panel P05
 | Onsite Diagnostic testing of Power Transformers for Condition-Health Assessment | Under Wide Circulation | Working Panel P09
 | Voltage Regulating Distribution Transformers | Under Review | Working Panel
 | Transformers for Static Converters | Under Review | Working Panel
 | Solid State Transformers | Under Review | Working Panel

## Slide 4: PROGRESS OF NWIP’S AGAINST THE ANNUAL ACTION PLAN FOR 2024-2025 AND THE PROCESS ADOPTED
SECTIONAL COMMITTEE | SUBJECT/TITLE OF NWIP | STATUS | PROCESS
ETD 34-Instrument Transformers | Condition Monitoring of Instrument Transformers | Working draft under preparation | Working Panel P01
 | Maintenance and Installation of Instrument Transformers | Working draft under preparation | Working Panel P03

## Slide 5: NWIP STATUS
Sectional Committee | No. of NWIP as per APS 2024-2025 | Status of NWIP
ETD 02 | 4 | Published -03 Under Review-1
ETD 16 | 8 | Under WC-1 Working Draft under Preparation-4 Under Review-3
ETD 34 | 2 | Working Draft under Preparation-2

## Slide 6: PROGRESS OF REVIEWS AGAINST THE ANNUAL ACTION PLAN FOR 2024-2025
Sectional Committee | Standards due for Review |  | Review Completed |  | Review under Progress |  | Outcome of Review |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | Revised |  | Reaffirmed |  | Amended |  | Withdrawal |  | Archived |  | Total | 
 | Pre 2K | Post 2K | Pre 2K | Post 2K | Pre 2K | Post 2K | Pre 2K | Post 2K | Pre 2K | Post 2K | Pre 2K | Post 2K | Pre 2K | Post 2K | Pre 2K | Post 2K | Pre 2K | Post 2K
ETD 02 | 65 | 32 | 6 | 21 | 52 | 11 | 7 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 21
ETD 16 | 13 | 12 | 10 | 6 | 3 | 6 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 5
ETD 34 | 5 | 11 | 5 | 10 | 0 | 1 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 10

## Slide 7: Process adopted for review of standards
Sectional Committee | No. of Standards taken up for Review as per APS (2024-2025) | Process Adopted for Review (ARP/WG/WP/R&D/ Workshop/Interns) | No. of Projects done without ARP or WG/WP | Process adopted for projects done without ARP or WG
ETD 02 | 104 | ARP-50 WP- 25 Interns-8 | 21 (Post 2K) | The standards under Column 4 are adopted from IEC. These have been reviewed by the committee and the committee decided that no change is required in those standards. Also, there is no change in the status of the corresponding base IEC standards. Hence it has been decided to reaffirm the standards. However, the same will be reviewed again whenever the corresponding base IEC standards gets revised. Experts will be designated from India whenever the corresponding base IEC standards are taken up for revision at IEC.
ETD 16 | 25 | ARP-1 WP-18 Interns-1 | 5 (Post 2K) | 
ETD 34 | 16 | ARP-0 WP-5 Interns-0 | 11 (Post 2K) | 

## Slide 8: WORKING PANELS AND WORKING GROUPS
Sectional Committee | No. of existing Working Panels and Working Groups | Title of Working Panels (WP) and Working Groups (WG) | No. of Working Panels/Groups created | No. of Working Panels/Groups abolished | Plan of Action
ETD 02 | Working Panels-5 Working Groups-0 | Cellulosic/Non-Cellulosic Papers and Fabrics Polymeric/Elastomeric Insulation and Ceramics Resins and Varnishes Revision of IS 15652 Formulation of New Standard on Heat Shrinkable Sleeves | Working Panels-3 Working Groups-0 | Working Groups-4 | Working Panels/Groups will be restructured in line with the sectorial classification of the Sectional Committees.
ETD 16 | Working Panels-11 Working Group-1 | Dry Type Distribution Transformers-WP Repair of Distribution Transformers-WP Transformer Fittings & Accessories-WP | Working Panels-0 Working Groups-0 | Working Panels-0 Working Groups-0 | Working Panels/Groups will be restructured in line with the sectorial classification of the Sectional Committees.

## Slide 9: WORKING PANELS AND WORKING GROUPS
Sectional Committee | No. of existing Working Panels and Working Groups | Title of Working Panels (WP) and Working Groups (WG) | No. of Working Panels/Groups created | No. of Working Panels/Groups abolished | Plan of Action
ETD 16 | Working Panels-11 Working Group-1 | d. Tap Changers-WP e. Inverter Duty Transformers-WP f. On-Site Diagnostic testing for condition/health assessment of Power Transformers-WP g. Self Protection/Disconnection devices for distribution transformers-WP h. Interpretation/Clarification on Indian Standards-WP i. Revision of IS 10028 Series-WP j. Revision of IS 1180 (Part 1)-WP k. Submersible Duty Transformers and Accessories-WP l. Revision of IS 1180 (Series)-WG | Working Panels-0 Working Groups-0 | Working Panels-0 Working Groups-0 | Working Panels/Groups will be restructured in line with the sectorial classification of the Sectional Committees

## Slide 10: WORKING PANELS AND WORKING GROUPS
Sectional Committee | No. of existing Working Panels and Working Groups | Title of Working Panels (WP) and Working Groups (WG) | No. of Working Panels/Groups created | No. of Working Panels/Groups abolished | Plan of Action
ETD 34 | Working Panels-3 Working Groups-0 | Condition Monitoring of Instrument Transformers. Revision of IS 4146:1983, IS 4201:1983, IS 5547:1983, IS 6949:1973 and IS 16227 (Part 1):2016 Maintenance & Installation of Instrument Transformers | Working Panels-1 Working Groups-0 | Working Panels-0 Working Groups-0 | Working Panels/Groups will be restructured in line with the sectorial classification of the Sectional Committees.

## Slide 11: IEC Projects
IEC TC | NMC | New Projects (NP) | Title of the Project | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 14-Power Transformers | ETD 16 | 14/1102/NP | Technical guideline for the Application, Specification, and Testing of Phase-Shifting Transformers | Medium | Mr. Rajaram Mohan Rao Chennu, CPRI Bengaluru | Identification based on the Sector relevance of the Project. Discussion in the Committee Identification & Recommendation by the Committee members. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.
 |  | 14/1115/CD | Power transformers - Part 1: General | High | a. Mr. Rajaram Shinde (In Personal Capacity) b. Mr. Kapil Sharma, ERDA, Vadodara c. Mr. Nagarjuna Babu Nannapaneni, Individual Capacity d. Mr. Abinash Bordoloi, BIS | 
 |  | 14/1114/CD | Power transformers - Part 2: Temperature rise for liquid- immersed transformers | High | a. Mr. Rajaram Mohan Rao Chennu, CPRI Bengaluru b. Mr. Kapil Sharma, ERDA, Vadodara | 

## Slide 12: IEC Projects
IEC TC | NMC | New Projects (NP) | Title of the Project | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 14-Power Transformers | ETD 16 | 14/1079/CD | Power transformers - Part 5: Ability to withstand short circuit | High | a. Mr. Moorkath Vijayakumaran Personal capacity) (In b. Mr. Rajaram Mohan Rao Chennu, CPRI Bengaluru c. Mr. Ramesh K Patel, National High Power Test Laboratory Pvt. Ltd, Sagar | Identification based on the Sector relevance of the Project. Discussion in the Committee Identification & Recommendation by the Committee members. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.
 |  | 14/1123/CD | Power transformers - Part 6: Reactors | High | Mr. C Jayasenan, Siemens Limited, Mumbai | 

## Slide 13: IEC Projects
IEC TC | NMC | New Projects (NP) | Title of the Project | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 38-Instrument Transformers | ETD 34 | 38/792/NP | Instrument transformers - Part 201: General requirements for Instrument Transformers for low voltage applications (≤1000 V AC and 1500 V DC) | High | a. Mr. Mayank Yadav, GE (T & D) India Limited, Noida b. Mr. Chetas Parikh, Narayan Powertech Pvt. Ltd, Vadodara | Identification based on the Sector relevance of the Project. Discussion in the Committee Identification & Recommendation by the Committee members. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.
 |  | 38/793/CD | Instrument transformers - Part 7: Specific requirements for electronic Voltage Transformers | Medium | a. Mr. Mayank Yadav, GE (T & D) India Limited, Noida b. Mr. Vrajesh J Desai, In Individual Capacity | 
 |  | 38/794A/CD | Instrument transformers - Part 8: Specific requirements for Electronic Current Transformers | Medium | a. Mr. Mayank Yadav, GE (T & D) India Limited, Noida b. Mr. Vrajesh J Desai, In Individual Capacity | 

## Slide 14: IEC Projects
IEC TC | NMC | New Projects (NP) | Title of the Project | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 38-Instrument Transformers | ETD 34 | 38/802/CD | Instrument Transformers integrated with other devices - Requirements and tests | Medium | Mr. Pradeep Deshpande, Gilbert and Maxwell Transformers Pvt. Ltd, Nashik | Identification based on the Sector relevance of the Project. Discussion in the Committee Identification & Recommendation by the Committee members. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.
 |  | 38/797/CD | Instrument transformers - Part 14: Additional requirements for current transformers for DC applications | Medium | Mr. Mayank Yadav, GE (T & D) India Limited, Noida | 
 |  | 38/798/CD | Instrument transformers - Part 15: Additional requirements for voltage transformers for DC applications | Medium | a. Mr. Mayank Yadav, GE (T & D) India Limited, Noida. b. Mr. Sunil Nannaware, Hitachi Energy India Ltd., Bangalore | 

## Slide 15: IEC Projects
IEC TC | NMC | New Projects (NP) | Title of the Project | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 38-Instrument Transformers | ETD 34 | 38/799/CD | Instrument transformers - Part 2: Additional requirements for current transformers | High | a. Mr. G. V Akre, Hivoltrans, Gujarat b. Ms. Geeta Joshi, Hitachi Energy India Ltd., Bangalore c. Mr. Chetas Parikh, Narayan Powertech Pvt. Ltd, Vadodara d. Mr. Vrajesh J Desai, In Individual Capacity | Identification based on the Sector relevance of the Project. Discussion in the Committee Identification & Recommendation by the Committee members. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.
 |  | 38/800/CD | Instrument transformers - Part 3: Additional requirements for inductive voltage transformers | High | a. Mr. G. V Akre, Hivoltrans, Gujarat b. Mr. Chetas Parikh, Narayan Powertech Pvt. Ltd, Vadodara c. Mr. Vrajesh J Desai, In Individual Capacity | 

## Slide 16: IEC Projects
IEC TC | NMC | New Projects (NP) | Title of the Project | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 38-Instrument Transformers | ETD 34 | 38/801/CD | Instrument transformers - Part 5: Additional requirements for capacitor voltage transformers | High | a. Mr. Mahesh Dorlikar, Hitachi Energy India Ltd., Bangalore b. Mr. Vrajesh J Desai, In Individual Capacity | Identification based on the Sector relevance of the Project. Discussion in the Committee Identification & Recommendation by the Committee members. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.
 |  | 38/715/CD | Amendment 1 - Instrument transformers - Part 9: Digital interface for instrument transformers | Medium | a. Mr. Pradeep Deshpande, Gilbert and Maxwell Transformers Pvt. Ltd, Nashik b. Mr. Mahesh Dorlikar, Hitachi Energy India Ltd., Bangalore | 

## Slide 17: IEC Projects
IEC TC | NMC | New Projects (NP) | Title of the Project | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 112-Evaluation and Qualification of Electrical Insulating Materials and Systems | ETD 02 | 112/628/NP | Electrical insulating Materials and Systems- DC Voltage Endurance Evaluation | High | a. Ms. Sneha Sheth, ERDA, Vadodara b. Ms. Ashitha Parambalath Narendran, CPRI Bengaluru | Identification based on the Sector relevance of the Project. Discussion in the Committee Identification & Recommendation by the Committee members. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.
 |  | 112/644/NP | Evaluation of hydrophobicity retention of polymeric insulating materials under high voltage stress with the dynamic drop test. | High | a. Ms. Sneha Sheth, ERDA, Vadodara b. Ms. Ashitha Parambalath Narendran, CPRI Bengaluru c. Dr. Palash Mishra, NIT Warangal | 

## Slide 18: IEC Projects
IEC TC | NMC | New Projects (NP) | Title of the Project | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 112-Evaluation and Qualification of Electrical Insulating Materials and Systems | ETD 02 | 112/643/CDV | Method for the determination of the proof and the Comparative tracking indices of solid insulating materials | High | a. Ms. Sneha Sheth, ERDA, Vadodara b. Ms. Ashitha Parambalath Narendran, CPRI Bengaluru | Identification based on the Sector relevance of the Project. Discussion in the Committee Identification & Recommendation by the Committee members. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.
 |  | 112/654/CD | Recommended test methods for determining the relative resistance of insulating materials to breakdown by surface discharges | High | a. Ms. Sneha Sheth, ERDA, Vadodara b. Ms. Ashitha Parambalath Narendran, CPRI Bengaluru | 
 |  | 112/635/CD | Electrical insulating materials -Thermal endurance properties - Part 1: procedures evaluation results Ageing and of test | High | a. Ms. Sneha Sheth, ERDA Vadodara b. Dr. Nilesh Pandya, Electrical Testing Centre, Vadodara | 

## Slide 19: IEC Projects
IEC TC | NMC | New Projects (NP) | Title of the Project | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 112-Evaluation and Qualification of Electrical Insulating Materials and Systems | ETD 02 | 15/986/NP | Specification for cellulosic papers for electrical purposes – Part 3: Specifications for individual materials – Sheet 6: Press paper | Medium | Ms. Sneha Sheth, ERDA Vadodara | Identification based on the Sector relevance of the Project. Discussion in the Committee Identification & Recommendation by the Committee members. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.
 |  | 15/1034/CDV | IEC 60684-2 ED4 Flexible insulating sleeving - Part 2: Methods of test | High | a. Ms. Sneha Sheth, ERDA Vadodara b. Ms. Ashitha Parambalath Narendran, CPRI Bengaluru | 

## Slide 20: SC/WP Meetings planned and held outside hq
SC meetings planned for organizing outside hQ
ETD 16 Sectional Committee Planned at MOU Partner institutes in December/January 2025.

## Slide 21: Status of process reform measures
Attendance in sectional committee meetings
Inactive Members- Identified after every sectional committee meetings and removed if found absent in two consecutive meetings.
Comments on p-drafts- no p-drafts circulated.
Resolutions-circulated to the members after every sectional committee meetings.
Members trained- New members inducted in the committee are trained as and when trainings are conducted by nits.
Sc membership rationalized- evaluation of performance of committee members has been done based on Attendance, Comments on Drafts circulated, Comments on IEC documents circulated, contribution during the meetings based on which decision on membership will be taken during the upcoming sectional committee meetings.
Sectional Committee | Attendance in Q1 | Attendance in Q2
ETD 02 | 100 % | 93.75 %
ETD 16 | 85.19 % | 84.62 %
ETD 34 | 63.64 % | 58.33 %