## Slide 1: Management and Systems Department
Quality Management Sectional Committee MSD 2

## Slide 2: Annual Program for Standardization (APS) 2024-2025
Sl. No | TC. No. | NWIP | Standard under Review Carried Over Pre 2000 | Standard under Review Carried Over (Post 2000) | Standard under Review Current (Pre 2000) | Standard under Review Current (Post 2000)
1. | MSD 2 | 2 | 0 | 4 | 0 | 5

## Slide 3: PROGRESS OF REVIEWS AGAINST THE ANNUAL ACTION PLAN FOR 2024-2025
Sectional Committee | Standards due for Review |  | Review Completed |  | Review under Progress |  | Outcome of Review |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | Revised |  | Reaffirmed |  | Amended |  | Withdrawal |  | Archived | 
 | Pre 2K | Post 2K | Pre 2K | Post 2K | Pre 2K | Post 2K | Pre 2K | Post 2K | Pre 2K | Post 2K | Pre 2K | Post 2K | Pre 2K | Post 2K | Pre 2K | Post 2K
MSD 2 | 0 | 9 | 0 | 8 | 0 | 1 | 0 | 3 | 0 | 4 | 0 | 1 | 0 | 0 | 0 | 0

## Slide 4: NWIP STATUS & PROCESS ADOPTED (as per AAP 2024-25)
Sectional Committee | No. of NWIP as per APS 2024-2025 | Status of NWIP | Process adopted
MSD 02 | Management System Guideline Requirements for Social Welfare Schemes | Working Draft under Preparation | WG
 | Conformity Assessment Requirements for bodies providing validation and verification of social welfare schemes | Working Draft Prepared | WG

## Slide 5: REVIEW STATUS & PROCESS ADOPTED (as per AAP 2024-25)
Sectional Committee | Due for Review | Current Status of Review Standards | Progress of Reviews with break-up of Archived, Withdrawn, Reaffirmed, Amended and Revised. | Process adopted for the Reviews - ARP, WG, R&D, Workshop.
MSD 02 | 09 | Review Completed – 8 Under Review – 1 | Archived – 0 Withdrawn- 0 Reaffirmed – 4 Amended – 1 Revised – 3 | ARP – 0 WG – 8 R&D – 1

## Slide 6: Working Panels and Working Groups
Sl. No. | Sectional Committee | Active Working Panel | Active Working Groups | Abolished WG/WP
1. | MSD 02 | P11-Panel for Revision of IS 15700 2. P18- Panel for Scrutiny of documents pertaining to ISO/TC 176 | Formulation of Indian Standard on Management System Guideline Requirements for Social Welfare Schemes and Conformity Assessment Requirements for bodies providing validation and verification of social welfare schemes | MSD 2 :1 Subcommittee for Scrutiny of documents pertaining to ISO/TC 176 MSD 02 : 3 Subcommittee for Standards on Outsourcing P12 Panel for formulating Indian Guideline Standard on Outsourcing for manufacturing sector in alignment with ISO 37500 P15- Revision of IS 16677: 2017 P14 Composition of Panel to scrutinize the IPF Proposal P13- Panel for Strategic Action Plan P16- Revision of IS 16070: 2013 P20- Panel for ISO/TC/176/SC 3/Task Group 2- Potential Revision of ISO 10019:2005 Panel for Review of IS/ISO 19011: 2018, IS/ISO 18091:2024, IS/ISO 20700

## Slide 7: Experts in ISO Projects
S. No. | Committee | ISO/TC | Projects | Priority | Experts Identified (Y/N)
1. | MSD 2 | ISO/TC 176 | 4 | High -4 Medium - 0 Low - 0 | Y

## Slide 8: SC/WP meetings planned and held outside HQ.
Sl. No. | Sectional Committee | Meeting Planned | Partner Institute
1. | MSD 02 | 28.11.2024 | Malviya National Institute of Technology (MNIT) Jaipur

## Slide 9: Status of Process Reform measures
Committee | Attendance |  | Inactive Members Removed | Members trained
 | Pre Reform in 2023 | Post Reform in 2024 |  | 
MSD 02 | 52 % | 65 % | 16 | 9
Comments on P Drafts - NIL
Comments on WC-Drafts – 11 Comments received.
Resolutions-circulated to the members after every sectional committee meetings.
SC membership rationalized – Evaluation of performance of committee members is being done based on Attendance, Comments on Drafts circulated, Comments on ISO documents circulated, contribution during the meetings based on which decision on membership is being taken during the upcoming sectional committee meetings.