## Slide 1: REVIEW MEETING ​
Ms. Shubhanjali Umrao, Scientist-C
Chemical Department​
Member Secretary
Chemical Hazards Sectional Committee CHD 07,
Water Quality for Industrial Purposes Sectional Committee CHD 13 and
Water Quality Sectional Committee CHD 36​

## Slide 2: Progress of NWIPs and Process adopted for the NWIPs in CHD 07
S No. | Title of NWIP | Carried Over /Current | Mode of Proposal | Priority | Mode of Execution/ Process Adopted | Panel/Working Group to which ARP has been allocated | Current Status
1. | Nitrous Oxide- Code of Safety | Carried Over | Gas Industries Association | Grade 7 | Allocated as ARP | CHD 07: P5 | Under Print
2. | NWIP on Handbook of Loss Prevention | Current | Individual | Grade 7 | ARP | CHD 07: P1: WG1 | Working document is under preparation in working group
3. | NWIP Sodium Cyanide Code of Safety | Current | Ministry | Grade 7 | ARP | CHD 07: P3 | Working document is under preparation in working panel
4. | New Work Item Proposal on CHLORINE LEAKAGE KIT FOR TONNERS | Current | Manufacturer | Grade 7 | Intern followed by visit of MS to manufacturers firm to have better understanding of product | Working Group to be created to review the Pre standardization report submitted by intern and factory visit report submitted by MS for preparation of working document | Under Preparation

## Slide 3: Progress of NWIPs and Process adopted for the NWIPs in CHD 13, and CHD 36
S No. | Title of NWIP | Carried Over/Current | Mode of Proposal | Priority | Mode of Execution/ Process Adopted | Panel/Working Group to which ARP has been allocated | Current Status
1. | Specification for Condensate Feed Water and Steam once through supercritical boilers | Current | Technical Committee | Grade | ARP | CHD 13: P3 | Working document
2. | Semi-quantitative methods for the assessment of transparency of waters | Carried Over | Technical Committee | Grade 9 | ARP done by Committee Member |  | Published
3. | Detection of selected congeners of polychlorinated dibenzo-p-dioxins and polychlorinated biphenyls Method using a flow immunosensor technique in water and wastewater | Current | Technical Committee | Grade 9 | ARP done by Committee Member |  | WC Draft
4. | ISO/TS 5667-25:2022 Water quality — Sampling — Part 25: Guideline on the validation of the storage time of water samples | Current | Technical Committee | Grade 9 | ARP done by Committee Member |  | Under Preparation
5. | Method of test for determination of residual polyelectrolyte in water and wastewater | Current | Technical Committee | Grade 9 | R&D |  | Under Preparation

## Slide 4: Standard under review - carried over
Committee` | Due for Review = 5 |  |  |  |  | Pre 2000 = 7 |  |  |  | 
 | Under Preparation | WC Draft | Under Print | Published | Mode of execution | Under Preparation | WC Draft | Under Print | Published | Mode of execution
CHD 07 2024-2025 | 2 Post 2000 | - | - | 3 Pre 2000 | ARP to CHD 07:P3 2 | - | - | 7 | - | ARP to CHD 07:P6 7
 |  |  |  |  | ARP by MS followed by Industry Visit 1 |  |  |  |  | 
 |  |  |  |  | ARP to CHD 07:P7 2 |  |  |  |  | 
Total Pre 2000 – 59
Published – 11
Under Review- 23 (UP-7, WD-5, R&D-2)
Archived - 25

## Slide 5: Standard under review - carried over
Committee` | Due for Review = 3 |  |  |  |  | Pre 2000 = 3 |  |  |  | 
 | Under Preparation | WC Draft | Under Print | Published | Mode of execution | Under Preparation | WC Draft | Under Print | Published | Mode of execution
CHD 13 2024-2025 | 1 | - | 2 | - | ARP done by Committee Member 2 | - | - | 3 | - | ARP by MS 3
 |  |  |  |  | ARP done by MS followed by Industry Visit 1 |  |  |  |  | 
Total Pre 2000 – 24
Published – 14
Under Review- 9
Archived - 1

## Slide 6: Standard under review - carried over
Committee` | Due for Review = 0 | Pre 2000 = 8 |  |  |  | 
 |  | Under Preparation | WC Draft | Under Print | Published | Mode of execution
 |  | Under Preparation | WC Draft | Under Print | Published | Mode of execution
CHD 36 2024-2025 |  | 1 | 3 | 1 | 3 | ARP to CHD 36:P1 1 ARP to Committee Member 3 MS 4
Total Pre 2000 – 40
Published – 35
Under Review- 5 (WC-3, UP-1, UP-1)
Archived - 0

## Slide 7: Standard under review – Due for Review
Committee` | Due for Review 0 | Pre 2000 = 19 |  |  |  | 
 |  | Under Preparation | WC Draft | Under Print | Published | Mode of execution
CHD 07 2024-2025 |  | 19 Working Draft prepared -5 Working draft under preparation – 6 R&D – 2 ARP Allocated to BIS Officer 6 | - | - | - | ARP to CHD 07:P7 4 ARP to CHD 07:P6 2 R&D 2 Intern 2 Member Secretary 3 ARP Allocated to BIS Officer 6

## Slide 8: Standard under review - Due for Review
Committee` | Due for Review = 3 |  | Pre 2000 = 4 |  |  |  | 
 | Reviewed and Reaffirmed | Mode of execution | Under Preparation | WC Draft | Under Print | Published | Mode of execution
CHD 13 2024-2025 | 3 | ARP 3 | 4 | - | - | - | ARP to CHD 13:P1

## Slide 9: Standard under review - Due for Review
Committee` | Due for Review 1 |  | Pre 2000 1 |  | Other than Pre 2000 4 | 
 | WC Draft | Mode of execution | Published | Mode of execution | Underprint | Mode of execution
CHD 13 2024-2025 | 1 | ARP done by MS 1 | 1 | ARP done by Committee Member 1 | 4 | ARP done by Committee Member 3 MS 1

## Slide 10: Working Panels and Working Groups - Created, abolished, updated on Advance Dashboard
Panel/WG | Panel Name | Active/ Inactive | Creation Portal | Work Status | Duration | Work Allocated | Members
CHD 07 : P1 | Panel for revision of IS 1446:2002 Classification of Dangerous Goods CHD 07:P1 | Inactive | 02.07.2021 | - | Disbanded on 27.09.2024 | Revision of IS 1446 | 
CHD 07 : P7 | Panel on safety codes for chemicals under Group-I, CHD 07:P7 | Active | 02.08.2021 | Standing | 24 month | Revision IS 4644 : 1968, IS 4263 : 1967, IS 13910 : 1993, IS 4312 : 1967, IS 5302 : 1969 | 10 Academia -2 (IICT, NIT Trichy)
CHD 07 : P3 | Safety codes for chemicals | Active | 12.08.2021 | Standing | 24 month | Revision IS 5208 IS 6270 IS 4560, IS 8388 : 1977, IS 9278 : 1979, IS 5311 : 1969, IS 14631 : 1999 | 10 Academia -2 (IICT, NIT Trichy)
CHD 07 : P4 | Panel for revision of IS 4155:1966 | Inactive | 16.09.2021 | - | Disbanded on 27.09.2024 | Revision of IS 4155 | 
CHD 07 : P5 | Panel for Safe Practices for Storage and Handling of Nitrous Oxide | Inactive | 16.09.2021 | - | Disbanded on 27.09.2024 | Preparation of working document on nitrous oxide | 
CHD 07 : P6 | Panel on Industrial Gases - Code of Safety | Active | 16.09.2021 | Standing | 24 month | Revision of IS 5931 and its part | 6
CHD 07 : P8 | Panel to review the document received from ISO/TC 336 | Active | 14.09.2023 | Standing | 24 month | To review the document received from ISO/TC 336 | 5 Academia -2 (BIT Mesra)
CHD 07: WG1 | CHD 07: WG1 Handbook on loss prevention due to Chemical Hazards | Active | 14.09.2024 | Adoc | 6 months | To review the working document received in line with existing regulation and decide whether NWIP is required on the subject | 0

## Slide 11: Working Panels and Working Groups - Created, abolished, updated on Advance Dashboard
Panel/WG | Panel Name | Active/ Inactive | Creation Portal | Work Status | Duration | Work Allocated | Members
CHD 13:P1 | Water Treatment Technologies | Active | 21-01-2021 | Standing | 24 month | Revision IS 10392 : 1982, 1813 : 1961, 10392 : 1982, 10496 : 1983 | 10
CHD 13:P2 | Water Quality related to all types of Boilers | Active | 16-09-2021 | Standing | 24 month | Revision of 8188, 11491 | 09
CHD 13: P3 | Water Treatment Chemicals | Active | 16-09-2021 | Standing | 24 month | Revision of 13119 | 11

## Slide 12: Working Panels and Working Groups - Created, abolished, updated on Advance Dashboard
Panel/WG | Panel Name | Active/ Inactive | Creation Portal | Work Status | Work Allocated | Members
CHD 36: P1 | Revision of Standards based on new test method | Active | 2023-09-16 | Standing | To review Pre 2000 standard, and deliberate comments received on Pre 2000 standard | 8
CHD 36 : P2 | Panel for Formulation of Standard for Field Test Kits used for surveillance of drinking water | Inactive | 2022-06-17 | Disbanded | IS 18283 | 
CHD 36 : P2:WG1 | To prepare a document on subject Field Test Kit (FTKs) to be used for surveillance of drinking water | Inactive | 2022-10-12 | Disbanded | IS 18283 | 
CHD 36 : P3 | CHD 36 : P3 Testing and Sampling of Microplastics in Water and Wastewater | Active | 2023-05-29 | Standing | To review the document under development at ISO on sampling and method of test for determination of microplastic in water and wastewater | 4 (IIT Indore)

## Slide 13: ISO/IEC Expert
ISO Technical Committee | NMC | Title of the Project | New Projects (NP) | Level of Interest | Designated Expert | Strategies for identification of expert
TC 336 – Laboratory Design | CHD 07 | Laboratory design — Terms and definitions | ISO/CD 22544 | High | Dr. Arti Bhatt, Sc-F, CFEES Ms. Shubhanjali Umrao, Sc-C Dedicated Panel CHD 07 P8 | EoI hosted on social media handles such as LinkedIn Interaction with Professor in MoU Institutes during lecture sessions Segregation and Identification Based on Expertise Within the Committee Interaction During Visits to Industrial Units Use Google Patents to find the experts Recommendation by the Committee members and other empaneled experts. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.

## Slide 14: ISO/IEC Expert
ISO Technical Committee | NMC | Title of the Project | New Projects (NP) | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 147/SC 2 – Physical, chemical and biochemical methods | CHD 36 | Water Quality — Determination of total organic carbon for suspended solid containing water samples based on combined ultrasonic and alkaline extraction pretretment | ISO/CD 21027 | High | Shri N. Murali Mohan, Personal Capacity Ms Shubhanjali Umrao, Sc-C | EoI hosted on social media handles such as LinkedIn Interaction with Professor in MoU Institutes during lecture sessions Segregation and Identification Based on Expertise Within the Committee Interaction During Visits to Industrial Units Use Google Patents to find the experts Recommendation by the Committee members and other empaneled experts. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.

## Slide 15: ISO/IEC Expert
ISO Technical Committee | NMC | Title of the Project | New Projects (NP) | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 147/SC 2 – Physical, chemical and biochemical methods | CHD 36 | Water quality — Determination of dissolved chromium(VI) in water — Photometric method Water quality — Analysis of microplastic in water — Part 3: Thermo-analytical methods for waters with low content of suspended solids including drinking water | 1. ISO/DIS 18724 2. ISO/DIS 16094-3 | High High | Ms Noor Afshan Khan (Sc.-F NEERI) Ms Shubhanjali Umrao, Sc-C Ms. kiran Bala (Prof IIT Indore) | EoI hosted on social media handles such as LinkedIn Interaction with Professor in MoU Institutes during lecture sessions Segregation and Identification Based on Expertise Within the Committee Interaction During Visits to Industrial Units Use Google Patents to find the experts Recommendation by the Committee members and other empaneled experts. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.

## Slide 16: ISO/IEC Expert
ISO Technical Committee | NMC | Title of the Project | New Projects (NP) | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 147/SC 2 – Physical, chemical and biochemical methods | CHD 36 | Water quality — Estimation of measurement uncertainty based on validation and quality control data Water quality — Determination of adsorbable organically bound fluorine, chlorine, bromine and iodine (AOF, AOCl, AOBr, AOI) — Method using combustion and subsequent ion chromatographic measurement | 3. ISO/DIS 11352 (Ed 2) 4. ISO/DIS 18127 | High High | Ms Priti Amritkar, Director Labs Shri N. Raveendhar, Principal Scientist Shri N. Murali Mohan, Personal Capacity | EoI hosted on social media handles such as LinkedIn Interaction with Professor in MoU Institutes during lecture sessions Segregation and Identification Based on Expertise Within the Committee Interaction During Visits to Industrial Units Use Google Patents to find the experts Recommendation by the Committee members and other empaneled experts. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.

## Slide 17: ISO/IEC Expert
ISO Technical Committee | NMC | Title of the Project | New Projects (NP) | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 147/SC 5 – Biological methods | CHD 36 | Water quality — Determination of the toxicity of water samples on the embryo-larval development of Japanese oyster (Magallana gigas) and mussel (Mytilus edulis or M. galloprovincialis) Water quality — Sampling, capture and preservation of environmental DNA from water | ISO/DIS 17244 (Ed 2) ISO/DIS 17805 | Medium High | Ms Nivedita Sahu, Principal Scientist | EoI hosted on social media handles such as LinkedIn Interaction with Professor in MoU Institutes during lecture sessions Segregation and Identification Based on Expertise Within the Committee Interaction During Visits to Industrial Units Use Google Patents to find the experts Recommendation by the Committee members and other empaneled experts. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.

## Slide 18: ISO/IEC Expert
ISO Technical Committee | NMC | Title of the Project | New Projects (NP) | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 147/SC 5 – Biological methods | CHD 36 | Water quality — Determination of acute lethal toxicity to marine copepods (Copepoda, Crustacea) Water quality — Active biomonitoring method with in-situ caged benthic amphipods | ISO/CD 14669 ISO/CD TS 21738 | High High | Shri N. Raveendhar, Principal Scientist Shri N. Murali Mohan, Personal Capacity | EoI hosted on social media handles such as LinkedIn Interaction with Professor in MoU Institutes during lecture sessions Segregation and Identification Based on Expertise Within the Committee Interaction During Visits to Industrial Units Use Google Patents to find the experts Recommendation by the Committee members and other empaneled experts. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.

## Slide 19: ISO/IEC Expert
ISO Technical Committee | NMC | Title of the Project | New Projects (NP) | Level of Interest | Designated Expert | Strategy adopted for identification of expert
TC 147/SC 6 – Sampling (general methods) | CHD 36 | Water quality — Sampling — Part 10: Guidance on sampling of waste water Water quality — Sampling — Part 15: Preservation and handling of samples of sludge, sediment and suspended matter | ISO/CD 5667-10 ISO/CD 5667-15 | High High | Ms Noor Afshan Khan (Sc.-F NEERI) Shri N. Murali Mhan, Personal Capacity Ms Shubhanjali Umrao, Sc-C Shri N. Raveendhar, Principal Scientist Shri N. Murali Mohan, Personal Capacity | EoI hosted on social media handles such as LinkedIn Interaction with Professor in MoU Institutes during lecture sessions Segregation and Identification Based on Expertise Within the Committee Interaction During Visits to Industrial Units Use Google Patents to find the experts Recommendation by the Committee members and other empaneled experts. Decision taken in the Sectional Committee meeting after examination of the profiles submitted by the expert.

## Slide 20
TC STAKEHOLDER’S RATIONALIZATION
CHD 07 | CHD 13 | CHD 36
Central Ministry - 07 Regulatory Body - 02 R&D Organization - 07 Academic Institution - 02 Industry Association - 06 Industry - 02 Technologist - 1 Expert – 02 CHD 07-29 | Central Ministry – 05 State Government - 01 R&D Organization - 04 Industry Association - 02 Industry - 05 Technologist - 02 Expert – 03 CHD 13 - 22 | Central Ministry - 06 R&D Organization - 06 Academic Institution - 01 Industry Association - 03 Industry - 04 Technologist - 2 Expert – 01 CHD 36- 23
Vacancy |  | 
R&D Organization - 2 Academic Institution - 2 | Academic Institution - 0 Regulatory Body - 0 Expert - 0 | R&D Organization - 2 Academic Institution - 1

## Slide 21: SC/WP Meetings planned and held outside BIS HQ
CHD 07 Chemical Hazards Sectional Committee |  |  |  |  |  | 
Sl No. | Meeting No. | Meeting Date | Mode | Venue | Resolution Circulated (Within 24 hr) | Attendance Percent
1 | 13 | 16/04/24 | Hybrid Meeting | BIS HQ New Delhi | Yes | 89.29 %
2 | 14 | 27/09/24 | Hybrid Meeting | BIS HQ New Delhi | Yes | 85.71 %
3 | 15 | 22/11/24 | Hybrid Meeting | NIT Trichy | - | 
4 | 16 | 16/02/25 | Physical Meeting | NSC, Mumbai | - | 
CHD 13 Water Quality For Industrial Purposes Sectional Committee |  |  |  |  |  | 
Sl No. | Meeting No. | Meeting Date | Mode | Venue | Resolution Circulated | Attendance Percent
1 | 32 | 04/07/24 | Hybrid Meeting | BIS HQ New Delhi | Yes | 90 %
2 | 33 | 29/10/24 | Hybrid Meeting | BIS HQ New Delhi | - | 
3 | 34 | 27/02/25 | Physical Meeting | BARC, Mumbai | - | 
CHD 36 Water Quality Sectional Committee |  |  |  |  |  | 
Sl No. | Meeting No. | Meeting Date | Mode | Venue | Resolution Circulated | Attendance Percent
1 | 20 | 25/06/24 | Hybrid Meeting | BIS HQ New Delhi | Yes | 92 %
2 | 21 | 18/09/24 | Hybrid Meeting | Central Laboratory , Ghaziabad, Uttar Pradesh, India | Yes | 87.5 %
3 | 22 | 19/12/24 | Hybrid Meeting | EPTRI, Hyderabad | - | 
4 | 23 | 20/03/25 | Hybrid Meeting | Venue to be decided | - | 

## Slide 22: Status of process reform measures
Inactive Members
Identified after every sectional committee meetings and removed if found absent in two consecutive meetings.
CHD 07-1 inactive member removed
Comments on P-drafts
Members trained
New members inducted in the committee are trained as and when trainings are conducted by NITS.
Committee | No of P draft | No of Commenter
CHD 07 | 1 | 4
CHD 36 | 1 | 17
SC membership rationalized
:
Evaluation of performance of committee members has been done based on Attendance
Comments on Drafts circulated
Comments on IEC documents circulated
Contribution during the meetings based on which decision on membership will be taken during the upcoming sectional committee meetings.
Evaluation of performance of committee members has been done based on Attendance
Comments on Drafts circulated
Comments on IEC documents circulated
Contribution during the meetings based on which decision on membership will be taken during the upcoming sectional committee meetings.

## Slide 23: Thank You