## Slide 1
MID-year review MHD 02 - Orthopedic Instruments, Implants and Accessories MHD 13 - Veterinary Hospital Planning and Surgical Instruments MHD 14 - Hospital Planning Sectional Committee
Vinit Vidyadhar Bansod
Scientist-C

## Slide 2: PROGRESS OF NWIP AGAINST APS 2024-25 AND THE PROCESS ADOPTED
SECTIONAL COMMITTEE | SUBJECT/TITLE OF NWIP | STATUS | PROCESS
MHD02 - Orthopedic Instruments, Implants and Accessories | 1) Battery Operated Dermatome | Working Draft Under Preparation | MHD 02 : P3 : WG1-Surgical Power Tools Working Group
 | 2) Battery Operate Drill | Working Draft Under Preparation | MHD 02 : P3 : WG1-Surgical Power Tools Working Group
 | 3) Pneumatic Drill | Working Draft Under Preparation | MHD 02 : P3 : WG1-Surgical Power Tools Working Group
 | 4) Arthroscopy Drill | Working Draft Under Preparation | MHD 02 : P3 : WG1-Surgical Power Tools Working Group
Notes: New ISO Subjects of interest
Published: 08
Under Print: 05
Final Draft: 10
Project Approval: 06

## Slide 3: PROGRESS OF NWIP AGAINST APS 2024-25 AND THE PROCESS ADOPTED (Contd.)
SECTIONAL COMMITTEE | SUBJECT/TITLE OF NWIP | STATUS | PROCESS
MHD 13 - Veterinary Hospital Planning and Surgical Instruments | Bovine Endometrium Cytotaping Catheter | To be wide circulated | Committee Consultation

## Slide 4: PROGRESS OF NWIP AGAINST APS 2024-25 AND THE PROCESS ADOPTED (Contd.)
SECTIONAL COMMITTEE | SUBJECT/TITLE OF NWIP | STATUS | PROCESS
MHD 14 - Hospital Planning Sectional Committee | Formulation of standard for Medical air-conditioning systems (Medical Aspects) | Proposal under consideration of Sectional Committee | MHD 14 : P3 : WG X (TBC)
 | Formulation of Standard on Ambulance (Medical Aspects) | Working Draft Under Preparation | MHD 14 : P3 : WG1-Ambulances (Medical Aspects) Working Group
 | Sustainability in Healthcare | Proposal under evaluation | MHD 14 : P4 : WG1-Sustainability in Healthcare Working Group
 | Standard for Pneumatic Transport System | Proposal under consideration of Sectional Committee | Committee
Notes: New ISO Subjects of interest
Published: 02
Under Print: 02
Final Draft: 01
Project Approval: 02

## Slide 5: PROGRESS OF Review AGAINST APS 2024-2025
 |  | MHD02 | MHD02 | MHD13 | MHD13 | MHD14 | MHD14
 |  | Pre 2000 | Post 2000 | Pre 2000 | Post 2000 | Pre 2000 | Post 2000
Standards due for Review |  | 44 | 26 | 17 | 0 | 9 | 7
Review Completed |  | 43 | 25 | 17 | 0 | 6 | 3
Review under Progress |  | 1 | 1 | 0 | 0 | 3 | 4
Outcome of Review | Revised | 43 | 7 | 17 | 0 | 3 | 1
 | Reaffirmed | 0 | 18 | 0 | 0 | 0 | 2
 | Amended | 0 | 0 | 0 | 0 | 0 | 0
 | Withdrawal | 0 | 0 | 0 | 0 | 0 | 0
 | Archived | 0 | 0 | 0 | 0 | 3 | 0
 | Total | 43 | 25 | 17 | 0 | 6 | 3

## Slide 6: PROGRESS OF Review AGAINST APS 2024-2025
Sectional Committee | No. of Standards taken up for Review as per APS (2024-2025) | Process Adopted for Review (ARP/WG/WP/R&D/ Workshop/Interns) | No. of Projects done without ARP or WG/WP | Process adopted for projects done without ARP/WG
MHD 02 | Total: 70 Pre2000: 44 Post2000: 26 | Pre2000 06 - Interns 02 – Revision by ISO adoption 09 – under review ____________ Post2000 Nil | Pre2000 27 – Committee _____________ Post2000 18 (H)– Reaffirmation 08 (H) - Revision by adoption | Review of relevant & referred standards, documents, guidelines etc. by the member secretary. Committee consultation – Manufacturers, R&D bodies and users Review of Indian Standards/ relevant ISO standards by the identified committee members. Recommendation of committee.
MHD 13 | 17 | WG | - | 
MHD 14 | Total: 16 Pre2000: 09 Post2000: 07 | WG | - | 

## Slide 7: Working Panels and Working Groups
TC | Sectors | Sub-sectors | Panel created | Sub subsectors | Working Group created
MHD 02 | Orthopedic | Orthopedic Implants | P1 | Materials for Implants | TBC
 |  |  |  | Hip, Knee, and Other Joint Replacement | TBC
 |  |  |  | Osteosynthesis and spinal devices | TBC
 |  | Orthopedic Surgery Instruments | P2 | Bone and Pin Handling Instruments & Reconstruction Sets (screws, pins, plates, nails, wires etc.) | WG 1: Reconstruction Sets
 |  |  |  | Cervical Collars | TBC
 |  |  |  | Clamps, Forceps, and Graspers | TBC
 |  |  |  | Chisels, Osteotomes, and Gouges | TBC
 |  |  |  | Bone Saws, Mallets, and Rasps (non-power) | TBC
 |  |  |  | Orthopaedic Instruments (General) | TBC
 |  | Orthopedic Surgical Powertools | P3 | Surgical Drills, Drivers & Saws | WG 1: Surgical Power Tools
 |  |  |  | Reamers, Burrs, Dermatomes | TBC
 |  |  |  | Shavers and De-Briders | TBC

## Slide 8: Working Panels and Working Groups
TC | Sectors | Sub-sectors | Panel created | Sub subsectors | Working Group created
MHD 13 | Veterinary | Veterinary Hospital Planning | P1 | --- | WG1 : General Requirements for Veterinary Hospitals
 |  | Veterinary Surgical Instruments | P2 | --- | WG1: Revision of IS on Veterinary Castrator
 |  | Veterinary Ophthalmological Instruments | TBC | --- | 

## Slide 9: Working Panels and Working Groups
TC | Sectors | Sub-sectors | Panel created | Sub subsectors | Working Group created
MHD 14 | Hospital Planning | Hospital Planning | P3 | Specific Facilities | WG1 : Ambulances (Medical Aspects)
 |  |  |  | Hospital Infrastructure Planning | TBC
 |  | Healthcare Quality Management | P4 | Healthcare Organization Quality Management | WG1 : Sustainability in Healthcare
 |  |  |  | Quality Management in Hospital Services | TBC
 |  | Medical Laboratory Quality Management | P5 | Point-of-Care and In Vitro Diagnostics | TBC
 |  |  |  | Quality and Competence | TBC
 |  |  |  | Safety and Risk Management | TBC
 |  |  |  | Sample Collection and Handling | TBC
 |  |  |  | Susceptibility Testing | TBC

## Slide 10: Working Panels and Working Groups
TC | Sectors | Sub-sectors | Panel created | Sub subsectors | Working Group created
MHD 14 | Hospital Planning | Medical Devices Quality Management | P6 | Medical Device Software and Technology | TBC
 |  |  |  | Connectors and Specific Device Components | TBC
 |  |  |  | Symbols and Usability Engineering | TBC
 |  |  |  | Quality and Risk Management of Medical Devices | TBC

## Slide 11: ISO/IEC Projects - Identified in H & M category, experts designated, strategies adopted to identify experts.
Sl. No. | Committee / Working Group | Reference | English title | Priority (H/M) | Designated Expert:
1 | ISO/TC 212 | ISO/TS 16782:2016 (vers 2) | Clinical laboratory testing — Criteria for acceptable lots of dehydrated Mueller-Hinton agar and broth for antimicrobial susceptibility testing | Level M | Dr. Sujatha Chandrasekaran, NABL Syed Tahira Rizvi, Asst Director, NABL
2 | ISO/TC 212 | ISO 18153:2003 (vers 4) | In vitro diagnostic medical devices — Measurement of quantities in biological samples — Metrological traceability of values for catalytic concentration of enzymes assigned calibrators and control materials | Level H | Dr. Swathi Sudhakar (IIT Madras) Pankaj Johri , Director NABL
3 | ISO/TC 212 | ISO 20776-1:2019 (Ed 2) | Susceptibility testing of infectious agents and evaluation of performance of antimicrobial susceptibility test devices — Part 1: Broth micro-dilution reference method for testing the in vitro activity of antimicrobial agents against rapidly growing aerobic bacteria involved in infectious diseases | Level H | Dr. Swathi Sudhakar (IIT Madras) Dr. Sujatha Chandrasekaran Syed Tahira Rizvi, Asst Director NABL

## Slide 12
Sl. No. | Type | Committee / Working Group | Reference | English title | Priority (H/M) | Designated Expert:
4 | SR | ISO/TC 212 | ISO 20916:2019 | In vitro diagnostic medical devices — Clinical performance studies using specimens from human subjects — Good study practice | Level H | Ms Gayathri S, Jt. Director NABL
5 | CD | ISO/TC 212 | ISO/CD 22367 | Medical laboratories — Application of risk management to medical laboratories | Level H | Pankaj Johri, Director NABL Ms Gayathri S, Jt. Director NABL
6 | NP | ISO/TC 212 | ISO/NP 21474-4 | In vitro diagnostic medical devices — Multiplex molecular testing for nucleic acids — Part 4: Detection of pathogens | Level H | Haribabu, Deputy Director, NABL
7 | NP | ISO/TC 212 | ISO/NP 25379-1 | In vitro diagnostic Next Generation Sequencing (NGS) workflows — Part 1: Part 1: Human DNA examination | Level H | Ms Gayathri S, Jt. Director NABL Haribabu, Deputy Director, NABL

## Slide 13
Sl. No. | Type | Committee / Working Group | Reference | English title | Priority (H/M) | Designated Expert:
8 | NP | ISO/TC 212 | ISO/NP 25391-2 | In vitro diagnostic Next Generation Sequencing (NGS) workflows — Part 2: Part 2: Human RNA examination | Level H | Ms Gayathri S, Jt. Director NABL Haribabu, Deputy Director, NABL
9 | NP | ISO/TC 304 | ISO/NP 25268 | Guidelines for Hospital Internal Logistics Services using Autonomous Mobile Robots | Level M | Pankaj Johri, Director NABL Shweta Sinha, Dy Director NABL
10 | CD | ISO/TC 304 | ISO/CD 20364 | Healthcare organization management — Guidance for healthcare organizations’ response to the surging diagnostic demands in a pandemic | Level H | Pankaj Johri, Director NABL Dr Mitali, Assst Director, NABL

## Slide 14: Strategies Adopted To Identify Experts: Sensitization of MoU institutes & committee members on need for project wise mapping of experts. Focused emails to MOU institutes and relevant Academic Institutes Opportunity given to experts who are not committee members.
Sl. No. | Type | Committee / Working Group | Reference | Priority (H/M) | Designated Expert
11 | DIS | ISO/TC 150/SC 1 | ISO/DIS 23317 (Ed 4) Implants for surgery — In vitro evaluation for apatite-forming ability of implant materials | Level H | Dr Kantesh Balani, IIT Kanpur
12 | SR | ISO/TC 150/SC 4 | ISO 14243-5:2019 Implants for surgery — Wear of total knee prostheses — Part 5: Durability performance of the patellofemoral joint | Level H | Dr Vamsi K Balla, CSIR-CGCRI
13 | SR | ISO/TC 150/SC 4 | ISO 22622:2019 Implants for surgery — Wear of total ankle-joint prostheses — Loading and displacement parameters for wear-testing machines with load or displacement control and corresponding environmental conditions for test | Level H | Dr Vamsi K Balla, CSIR-CGCRI

## Slide 15: SC/WP meetings planned and held outside HQ. SC/Panel/WG Meetings Held Outside HQ in Q1 and Q2 : Nil
Sl. No. | Technical Committee | Venue | 
1) | MHD02 | Yet to be finalized | Q4
2) | MHD13 | Tamil Nadu Veterinary and Animal Sciences University, Chennai | Q3
3) | MHD14 | Yet to be finalized | Q4
4) | 2nd meeting of MHD 13 : P1 - Veterinary Hospital Planning Panel | College of Veterinary Science and Animal Husbandry, Mhow | December (Tentative)

## Slide 16: Committee Composition – MHD 02
Chart: Total:
| Industry Association | R&D Organization | Academic Institution | Regulatory Body | Industry
Sales | 1 | 4 | 2 | 1 | 5
Attendance in Q1: 93.33%
Attendance in Q2: 80.00%
Inactive members: Members are being identified and removed if found absent in two consecutive meetings.
Comments on P Drafts: No P-drafts
Resolutions: Discussed during the meeting and circulated on same day

## Slide 17: Committee Composition – MHD 13
Chart: Total:
| Industry Association | R&D Organization | Academic Institution | Industry | State Government | Regulatory Body
Sales | 1 | 2 | 5 | 1 | 2 | 3
Attendance in Q1: 77.78%
Attendance in Q2: 81.25%
Inactive members: Identified and removed if found absent in two consecutive meetings. 01 Organization removed
Comments on P Drafts: 03 Comments on 01 P Draft
Resolutions: Discussed during the meeting and circulated on same day

## Slide 18: Committee Composition – MHD 14
Chart: Total:
| Industry Association | R&D Organization | Academic Institution | Regulatory Body | Industry
Sales | 1 | 4 | 2 | 1 | 5
Attendance in Q1: 70.00%
Attendance in Q2: 88.24%
Inactive members: Identified and removed if found absent in two consecutive meetings.
Comments on P Drafts: No P-drafts
Resolutions: Discussed during the meeting and circulated on same day

## Slide 19
Thank you!

## Slide 20
BIS Awareness Workshop with Medical Colleges - Bharati Vidyapeeth Medical College
BIS Awareness Workshop with Medical Colleges – Dr D. Y. Patil Medical College
BIS Awareness Lecture to the research fellows of Biomaterial Department, IIT Kanpur on occasion of World Standards Day
Conducted a Two-day Capsule Course on Medical Device Quality and Risk Management at NITS